## Project Tracker
Create a Project Tracker in this worksheet. The title of this worksheet is in cell B1. Information about how to use this worksheet, including instructions for screen readers, is in the About worksheet. | Gantt Chart
The Start date can be manually input in cell D2, or use the template’s sample formula to find the smallest date in the milestone column from the milestone table below. |  | Start date: | 2019-07-01
The End date can be manually input in cell D3, or use the template’s sample formula to find the largest date in the milestone column from the milestone table below. |  | End date: | 2019-09-27
Information about the milestone table columns is in cells B4 to G4. | Enter a sequential set of numbers in the column below. | Enter the start date for the milestone or activity in the column below. | Enter the end date for the milestone or activity in the column below | Enter the milestone and/or activity description in the column below. This description will appear in the Project Chart. | Auto-calculated. The data below, under this column, is used for charting the milestones and activities. | Auto-calculated. Duration of each task
Table headings are in cells B5 to G5. There are two hidden columns: The Start-on day and Task Duration columns in cells F5 and G5 are auto-calculated and used for creating the Gantt Chart in the Gantt Chart worksheet. Sample data is in cells B6 to E21. The next instruction is in cell A22. | Position | Start Date | End Date | Milestone/Activity | Start-on day | Task Duration
| 1 | 2019-07-01 | 2019-07-12 | Project Scaffolding / Outline | 0 | 12
| 2 | 2019-07-15 | 2019-07-19 | Background, Aims, Objectives | 14 | 5
| 3 | 2019-07-22 | 2019-08-02 | Literature Review / Analysis | 21 | 12
| 4 | 2019-08-05 | 2019-08-30 | Software Development | 35 | 26
| 5 | 2019-09-02 | 2019-09-06 | Testing Complete | 63 | 5
| 6 | 2019-09-09 | 2019-09-13 | Critical Evaluation | 70 | 5
| 7 | 2019-09-16 | 2019-09-27 | Buffer Weeks / Final Write-Up | 77 | 12
| 8 | 2019-09-17 | 2019-09-27 | BCU Overlap | 78 | 11
To add more Milestones/Activities, insert new rows above this line
To add more milestones/activities, insert new rows above this line. This is the last instruction in this worksheet.

## Gantt chart
Gantt chart with a scrollbar is in this worksheet. Scrollbar starts in cell B29. This is the last instruction in this worksheet.

## Dynamic Chart Data Hidden (hidden)
Title of this worksheet is in cell B1. | Dynamic Chart Data
Horizontal scrolling increment heading is in cell B2. To manually increment the data, enter a new value in cell B3. The scrolling page auto-updates when the scrollbar is paged forwards or backwards in the Gantt Chart worksheet. | horizontal scrolling increment
Auto-updated Gantt Chart scrolling value is in cell B3. | 3
Table title is in cell B4. | Dynamic Data Table
Table headings are in cells B5 to E5. A note is in cell F5. This table will chart up to 5 milestones at one time. Do not modify or delete this worksheet or its contents. | milestone | date | Start-on day | duration | <--chart up to 5 milestones at a time
| Software Development | 2019-08-05 | 35 | 26
| Testing Complete | 2019-09-02 | 63 | 5
| Critical Evaluation | 2019-09-09 | 70 | 5
| Buffer Weeks / Final Write-Up | 2019-09-16 | 77 | 12
| BCU Overlap | 2019-09-17 | 78 | 11